## Ark2
Week 1 Planning

## Ark3
Lofthus Frukt og Saft
| Plan |  |  |  |  | Design |  |  |  |  | Build |  |  |  |  | Launch
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
Project Manager | Day 1: Client meeting, Business Proposal and Contract, Project Management; Day 6: Project Management, Present Research and Design Ideas to Client; Day 11: Project Management, Client Contact; Day 16: Project Management, Client Contact and Site Reveal
Project Manager Content Specialist | Day 1: First meeting
Project Manager Content Specialist Designer | Day 1: Goal Identification Needs Assessment Project Planning
Content Specialist Designer | Day 2: Researching
Project Manager Content Specialist Designer | Day 3: Strategic Planning
Content Specialist | Day 4: Content Planning
Content Specialist Front-End Developer Back-End Developer Designer | Day 5: Webiste outline/structure
Designer | Day 8: Draft Creative Consept, Styletiles, Moodboard; Day 11: Wireframe / Site Stucture
Content Specialist Copywriter | Day 8: Written Content Development
Photographer | Day 8: Photographing Portfolio Images; Day 11: Photographing Employees
Content Developer Designer | Day 12: UX/UI Planning and Testing; Day 16: UX/UI Testing
Front-End Developer Back-End Developer | Day 11: Writing code, Integrating and Site Building
Front-End Developer Back-End Developer | Day 17: Cross Platform and Browser Testing
Front-End Developer Back-End Developer | Day 18: Quality Check Validating
Content Specialist Front-End Developer Back-End Developer Designer | Day 19: Refinement
Project Manager Content Specialist Front-End Developer Back-End Developer Designer | Day 20: Launch